## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 51 | 2 |  |  |  | 14 | 2 | 2 | 3 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2016-10-31 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-17 | 2016-10-19 | 2016-10-21 | 2016-10-24 | 2016-10-26 | 2016-10-28 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 |  | Visuals | [23 empty] | Assigned
6 | 1 | Retexture Plane | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
7 | 1 | Split screen | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Verify?
8 | 1 | Trail renderer (no expiration) | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 2 | Powerup icons / models |  |  | 2 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 5 | Multiple maps? |  |  | 2 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
11 | 3 | Interesting implementation of map bounds | SS |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
12 | 2 | Water as bottom bound? | SS |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13
14
15
16 |  | Sounds
17 | 3 | Music | SS |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 3 | Plane propeller sound | SS |  | 1 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | decided against, was super annoying with 4 players
19 | 3 | Plane crash sound | SS |  | 1 | 1 | 0 |  | 1 | bar: 2016-10-17 to 2016-10-31
20 | 3 | Power up collect noise | SS |  | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 3 | Powerup use noises | SS |  | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 3 | Refuel noise | SS |  | 1 | 1 | 0 |  | 1 | bar: 2016-10-17 to 2016-10-31
23
24
25 |  | Gameplay
26 | 1 | Camera Follow | SS |  | 2 | 0 | 2 |  | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 1 | Plane physics | SS |  | 1 | 0 | 6 |  | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 1 | Plane controls (xbox) | SS |  | 3 | 0 | 5 |  | 3 | 3 | 3 | 3 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 1 | Powerup HUD/object |  |  | 2 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 3 | Stunts? |  |  | 2 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 1 | Trail collisions | SS |  | 4 | 0 | 5 |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32
33 |  | Powerups |  |  | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 2 | Invincibility |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 2 | Stealth |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 2 | Missile |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 2 | Dual trail |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38
39
40 |  | Menus
41 | 1 | Main menu | SS |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 2 | Color/Plane selection screen/controller select |  |  | 2 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 2 | Victory screen | SS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 |  | Tip line in-game | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45
46
47 | 1 | Research & Analysis | SS |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 2 | Justification Document | SS |  | 3 | 0 | 1 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 1 | Game Idea | SS |  | 3 | 0 | 4 |  | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 |  | Credits file | SS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 12 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 51 | 51 | 43.7143 | 36.4286 | 25.5 | 18.2143 | 10.9286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 24 | 24 | 22 | 17.5 | 10 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 6 | 6 | 6 | 6 | 6 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 |  |  | 3 | [5 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Shane Schulte | SS |  |  |  |  | SS | 41 | 41 | 39 | 34.5 | 27 | 22.5 | 11 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
223 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
236

## Daily Scrum
Producer | 2016-10-31 |  | Team Members
Approved | Dates |  | Shane Schulte
| 2016-10-17 | Mon | Fall Break
| 2016-10-18 | Tue | Fall Break
| 2016-10-19 | Wed | Done: Researched game ideas, didn't come up with much Next: Settle on a game idea
| 2016-10-20 | Thu | Done: Came up with a game idea, did preliminary research for document Next: Start making the game
| 2016-10-21 | Fri | Done: Found a free-to-use plane model, modified the texture to suit my needs (multiple colors) Next: Add physics/controls to the plane
| 2016-10-22 | Sat | football
| 2016-10-23 | Sun | Done: Started working on the controls, filled out the burndown chart (didn't realize it was needed for solo project), wrote the research & analysis paper, worked on physics/controls Next: Work on splitscreen
| 2016-10-24 | Mon | Scrapped a lot of the movement code, implemented trails
| 2016-10-25 | Tue | 485 project
| 2016-10-26 | Wed | 485 project
| 2016-10-27 | Thu | Controls finished, added in arena walls / water
| 2016-10-28 | Fri | Obtained music, started working on multiplayer aspects, lots of bugfixing
| 2016-10-29 | Sat | Added main menu system with multiplayer ready up configuration, added functionality for 2-4 player variable
| 2016-10-30 | Sun | Playtesting and added in fueling system, lots of refactoring to make it work with multiplayer, optimized trail code a bit
| 2016-10-31 | Mon | Wrote justification document/completed burndown chart/credits.txt, turned in completed build
| 2016-11-01 | Tue
| 2016-11-02 | Wed
| 2016-11-03 | Thu
| 2016-11-04 | Fri
| 2016-11-05 | Sat
| 2016-11-06 | Sun
| 2016-11-07 | Mon